## Sheet1
CRATIVE SOLUTIONS
ProjectName: AHC (User Web Application)
Started Date | 2020-07-30
Bug Id | Page Name | Test Steps | Bug Description | Expected Results | Actual Results | Tested Date | Pass / Fail / Not executed / Suspended | Priority | Status | Screen Shot or Screen Recorder details | Tested By | Developer Comments | Tester Comments | Re-Tested Date
Module Name: | Sign Up
AHCU01 | Sign Up | Launch>>Click on Sign up>>Click on Products | If user selected NUPCO account, based on this account we should display what products they have, but we are displaying all product details. And it should have droupdown and lable name. | We should display based on account we should display what products they have | Its displaying all products | 2020-07-30 | Fail | High | Open |  | Fazil
AHCU02 | Sign Up | Launch>>Click on Sign up>>Click on mobile number | If user given same mobile number for difrant users it is accepting and it should start with 5 only but if we give like 12345678 also its inserting data | Should display error massage | Successfully inserting data | 2020-07-30 | Fail | High | Open |  | Fazil
AHCU03 | Sign Up | Launch>>Click on Sign up>>Click on mobile number | If user given 8 digits as mobile number then also its accepting Ex:512345678 | Shoild accept only valid mobile numbers | Shoild accept only valid mobile numbers | 2020-07-30 | Fail | High | Open |  | Fazil
AHCU04 | Sign Up | Launch>>Click on Sign up>>Click on password | There is no connection between password and confirm password Ex: in password filed I have given 12345 and confirm I have given 11111 | Should display error massage | No validation between password and confirm password | 2020-07-30 | Fail | High | Open |  | Fazil
AHCU05 | Sign Up | Launch>>Click on Sign up>>Click on confirm password | There is no connection between confirm password and password Ex: in password filed I have given 12345 and confirm I have given 11111 | Should display error massage | No validation between password and confirm password | 2020-07-30 | Fail | High | Open |  | Fazil
AHCU06 | Sign Up | Launch>>Click on Sign up>>Click on select account | Same account name we are showing multypull times Ex: British -Saudi hosptical | Should not accept duplicate accounts | Should not accept duplicate accounts | 2020-07-30 | Fail | High | Open |  | Fazil
Module Name: | User
AHCU07 | User login | Login | User Email id: I have created a user as abc1@gmail.com for NUPCO account product as Edwards, and superuser admin also approved it but still I am unable to login with this ID pwd:12345 | Should able to login | Should able to login | 2020-07-30 | Fail | High |  |  | Fazil
AHCU08 | Change password | Login>>Click on Userprofile>>Click on change password | If user is entring invalid old password in this we should get error massage below the old password tab. | expecting valid error message | expecting valid error message | 2020-07-30 | Fail | High |  |  | Fazil
AHCU09 | Change password | Login>>Click on Userprofile>>Click on change password>>New password | If user is entring invalid password then user should get proper error massage Ex: confirm password should match with new password | expecting valid error message | expecting valid error message | 2020-07-30 | Fail | High |  |  | Fazil
AHCU10 | Change password | Login>>Click on Userprofile>>Click on change password | If user giving the password, but it is not as per our entry criteria, in this case, the user should get proper error message Ex: password should match with as we suggested | expecting valid error message | expecting valid error message | 2020-07-30 | Fail | High |  |  | Fazil
AHCU11 | Change password | Login>>Click on Userprofile>>Click on change password | "At least" spelling should corrct as of now we are showing as "Atleast" | At least spelling should corrct | At least spelling should corrct | 2020-07-30 | Fail | low |  |  | Fazil
AHCU12 | Tickets | loginn>>Click on tickets>>Click on new ticket>> click on system id/serial No droup dowin | I have created a user as hyd@gmail.com for NUPCO account product as zoll, and superuser admin also approved it and succesfully loged in with his account id and user wants to create a ticket but user unable to create a ticket becouse user don’t have seral no details in droupdowin list. | We should display based on account we should display what products they have | Its displaying all products | 2020-07-30 | Fail | High |  |  | Fazil
AHCU13 | Ticket list | loginn>>Click on tickets>>Click on ticket list>> | If user serched with Ticket Type and Status and user wants to clear scrch items in this case user don’t have such opstion should create | expecting Clear filter button | expecting Clear filter button | 2020-07-30 | Fail | High |  |  | Fazil